## Introduction
Cost Management Software Buyers Guide Worksheets
The following worksheets are meant to provide a place to start to help you define your business and functional requirements. It is intended to help you organize your requirements and gather fact-based information to determine which cost management software tool best meets your needs.
The example worksheets include:
Business Requirements
Required Functionality
Deployment Environment
For more information about ProjStream, visit www.projstream.com.
© 2023 ProjStream LLC, Revision August 16, 2023

## Business Requirements
Business Requirements
Ref. No.
1 | Issue | Project managers use ad-hoc Excel spreadsheets to manage budget, actual costs, and cost estimates for remaining work. Cost estimates lack details necessary to verify rationale. This limits the ability to create credible cost at completion forecasts for corporate financial analysis.
|  | Current State | Lack consistency in how project teams create and manage their budget data as well as track actual costs expended. Project teams lack direction on how to produce estimate to complete data.
|  | Requirement | Establish a central database for all project teams to maintain budget, actual cost, estimate to complete, and estimate at completion data. Tool should provide a collaborative working environment where all team members can manage and view the data as well as track changes.
|  | Expected Outcome | A significant increase in the consistency and quality of project time phased cost data for corporate financial analysis across business units. Eliminates manual process to collect and transform data from over 50 projects. Anticipate a reduction of at least 70% in the time required to produce financial reports.
2 | Issue | Unable to gather quantifiable data to determine resource availability and demand for existing projects as well as pending or likely contract awards. Business units are often lacking key resources that require temporary higher cost resources which impacts profit margins.
|  | Current State | Lack credible source data for resource planning and management. Business unit managers produce inconsistent ad-hoc Excel spreadsheets that lack substantiation.
|  | Requirement | Establish a central cost database to consistently produce time phased resource requirement data views for in process or planned project tasks across business units. Leverage resource profiles and learning curves to increase the accuracy of time phased resource requirements.
|  | Expected Outcome | Can routinely assess the likely resource demand to proactively manage resource requirements. Significantly increases resource planning predictability and accountability as well as employee retention. Anticipate a 60% reduction in temporary hires for surge support.
3 | Issue | Unable to proactively manage projects because of limited visibility into project status. Project manager progress assessments are often inconsistent and incomplete. This limits management’s ability to make timely decisions. Cost growth issues often surface without warning. The financial impacts are often significant and impact profit margins.
|  | Current State | Project teams use a mix of ad-hoc Excel spreadsheets and legacy tools to manage time phased cost data that are not integrated with the schedule tool. Project teams lack direction on how to define objective performance measures and how to proactively use them to the manage work effort. Project managers lack the tools needed to manage time phased cost data and produce performance metrics.
|  | Requirement | Establish a single cost management tool as a central database to maintain the time phased cost data. The tool must support industry standard methods for measuring work performance and calculate standard work performance metrics. The schedule and cost tools must be integrated to create schedule driven budget and estimate to complete data with schedule status as the basis for claiming performance.
|  | Expected Outcome | Incrementally improve management visibility into the current status of projects over the next 18 months. Enhanced process establishes the means to identify potential issues early so appropriate actions can be implemented quickly to mitigate or otherwise limit cost impacts to the projects. Reduce costly project surprises that adversely impact the company’s profit margins by 70% within that 18-month time frame.
4 | Issue
Current State
Requirement
Expected Outcome
Notes:
Identify how you intend to measure the impact of an issue in time or cost. Use the same measure to quantify the expected outcome by eliminating or reducing the impact of the issue. Use this data to calculate the return on investment and how quickly results can be achieved.

## Required Functionality
Required Functionality
Category | Functionality | Rating | Tool A | Tool B | Notes/Comments
Configuration, Setting Up Core Data
| Can establish a standard accounting calendar template | Required | Yes | Yes
| Projects can define specific reporting calendars as well as resource calendars | Required
| Can establish a standard base project configuration new projects can use as a template to enable cross-project reporting and analysis | Required
| Can create an unlimited number of user defined code lists and structures, add a variety of different types of user defined fields (text, codes, flags, Boolean, dates) to support project unique data views and reporting requirements | Required
| Can establish a standard rate template and rate calculations with ability to create custom expressions | Required
| Can build complex rate structures with ability to apply escalation factors | Required
| Can create an unlimited number of rate structures for different cost types (budget, actual costs, estimates) | Required
| Can import current rates from the accounting system | Required
| Can establish a standard hierarchical resource structure template with element of cost categories (labor, material, travel, other direct costs, subcontract) | Required
| Can easily import data from other systems using Excel | Required
Planning
Build WBS structure
Import WBS from Excel
Import WBS from scheduling system (identify specific tools such as Microsoft Project or Oracle Primavera P6)
Can produce a WBS dictionary
Can parse statement of work (SOW) document paragraphs into a code structure to map to WBS elements
Budgeting
Easy to use grid view similar to Excel to enter data with built-in hierarchical structure to view the data at summary, intermediate, and detail levels
Ability to change the order of the columns, hide or show columns, sort and filter the data in the grid view similar to Excel
Project team members can collaborate and share the cost data with optional user locks
Ability to import proposal cost estimate and basis of estimate (BOE) rationale as the initial basis for the time phased budget
Can enter budgets in hours, full time equivalents (FTEs), or cost and select the rate structure to apply direct and indirect rates
Can create custom budget distribution spreads and learning curves
Import resource loaded activity data from scheduling system to produce the time phased budget data
Ability to enter BOE, statement of work, and other text documentation with the budget data at user determined level of detail
Can create hierarchical bills of material (BOM)
Supports standard EVM techniques: 0/100, 100/0, 50/50, User Defined, Percent Complete, Earning Rules, Milestones, LOE, and Apportioned Effort
Supports rolling wave planning techniques
Built-in budget log to track management reserve and time phased budget changes
Can create a library of historical project performance data for future proposals and basis of estimates
Measuring Performance
Import schedule activity status as the basis for the work package performance claimed in the cost tool
Import actual costs from accounting system on a weekly and monthly basis
Enter estimated actuals for materials and subcontractors to align performance claimed and actual costs in the same accounting month
Analyzing Performance
Built-in cost data validation analysis view and report to identify common data anomalies
Import resource loaded activity data from scheduling system to produce the time phased estimate to complete (ETC) data
Web option for technical users or teaming partners to enter time phased ETC data
Web option for technical users or teaming partners to enter progress or percent complete when schedule is not integrated
Ability to do what-if analysis and create different ETC scenarios
Ability to enter or calculate an unlimited range of estimates at completion (EACs)
Calculates standard work performance and cost metrics
Reporting
Built-in ad-hoc and pivot table reporting
Easy to use built-in report wizard
Ability to establish report templates
Built-in element of cost reports including time phased resource planning reports, travel expense tracking reports
Ability to combine time phased cost data and documentation in one report
Single project, multi-project, or enterprise level portfolio analysis reporting
Workflow, Managing Changes
Ability to define user roles, routing rules and workflow queue to manage the development, entry, and maintenance of project data
Workflow available in the web to identify responsible parties for ETC or progress entry
Ability to manage baseline change requests and track them to closure
Ability to manage work authorization forms
Approved baseline change requests automatically update work authorization forms and budget log

## Deployment Environment
Deployment Environment
Security Requirements | Tool A | Tool B | Notes/Comments
SaaS subscription option available that is compliant with FedRAMP security requirements?
User access controls: Project level
User access controls: Role-based or user locking at WBS element level
User access controls: Subcontractor (external entity) specific grid view to enter or update data for specific WBS elements
Environment Details, Support Requirements |  |  | Notes/Comments
List other information the software vendor will need to price the software or to gain an understanding of likely costs you may incur to support the tool over time. Examples follow.
One or multiple locations? How many users at each location?
How many projects? What is the complexity and duration of the projects? Can the tool scale to support the smallest as well as the largest projects you have?
Single database?
What is built into the tool or are add-ons required? Do you need to purchase additional tools or utilities from the vendor to be able to meet your requirements?
What is the average release cycle for updates?
What is the average response and resolution time for software issues?
Does the software architecture support web services?
How easy is it to exchange data with other business systems?
How configurable is the tool?